# Guideline to Documentation for the Phase-II Upgrade Review Process

Prepared by:
M.Capeans, H. Chen, P.Farthouat, F.Lanni, L.Pontecorvo,  R. Vuillermet

# Introduction

This note specifies the documents that shall be made available for each stage of the review process. It shall be noted that the scope and expected content of the reviews have been specified elsewhere (EDMS 1979229), and it includes many aspects that are presented and scrutinized at the review but do not necessarily require formally approved documentation.

# SPR Documentation

The SPR verifies that complete written requirements exist, that they are sufficient to develop the designs, and specifications include sufficient opportunities for QC/QA. Specifications are compiled in a Specifications Document, which is internally reviewed in the project prior to the SPR, and formally released after a successful SPR.

Documentation to be made available for the SPR:

- Specification document

For detector/mechanical reviews, it is recommended to structure the Specifications Document as:

- Functional specification : description of the functions expected by the system to be designed

- Engineering specification : description of :

  - Performance values the design must fulfil (value, safety factor, acceptance value, etc.)

  - Loads that the system will face during its lifetime (from assembly to decommissioning) with explanation and justifications behind the values and selected metrics

  - Constrains of the design (physical, geometrical with envelop, etc.)

  - Interfaces of the system with other systems

For electronics reviews, a generic template for specification document is available for electronics components and assemblies, which can be found at EDMS 1770385. The electronics specification document should describe how the component will meet the requirements of the detector system and other critical items, particularly, the interfaces, level of radiation immunity and reliability considerations.

# PDR Documentation

The PDR verifies that prototype designs meet all aspects of the specifications documents. Technical feasibility of the design must be demonstrated, so simulations or partial prototypes demonstrating feasibility for critical functions are important. Furthermore, test plans shall show how the prototype devices will be tested to demonstrate functionality that meets the specification. Safety aspects of the design will be reviewed. Integration of the system into its environment will be verified and its installation feasibility will be assessed.

Documentation to be made available for the detector/mechanical PDR:

- The EDMS-approved Specification Document for the design to be reviewed is a requirement to hold a PDR.

- All technical description documents (Assembly, interface and integration drawings, design description, etc.)

- The test reports or simulation results and all documentation demonstrating the soundness of the design

- The approved envelop drawings or 3D model

Documentation to be made available for the electronics PDR:

- The EDMS-approved Specification Document for the design to be reviewed is a requirement to hold a PDR.

- All technical description documents (functional block diagram, key circuit design, interface definition, design description, etc.)

- Simulations or partial prototypes to demonstrate critical functions.

- Test plans to show how the prototype devices will be tested to verify functionality that meets the specification.

- Measures proposed to ensure reliability of component and/or system.

# FDR Documentation

The FDR reviews all the available data from prototypes to determine how well the design meets specifications. For components of a larger system, analysis and measurements demonstrating compatibility with external interfaces, consistent with specifications, are essential. Specifications documents should have been approved after SPR, and if applicable, modified and again approved after the PDR.

Documentation to be made available for the detector/mechanical FDR:

- Design information (e.g.: assembly drawings interface drawings, electrical or electronic scheme, etc.)

- Approved envelop drawing(s) or 3D model

- Integration plan of the system and its dependencies (e.g. services,)

- Installation sequence and procedure

- QA/QC documents (structured test plan and test infrastructure details)

- Production plan

- Procurement plan and procedures

- Overall schedule

- Approval documents for safety aspects, when required

Documentation to be made available for the electronics FDR:

- Design information (e.g.: schematics, layout including fabrication drawing and gerber, assembly package including assembly drawing and bill of materials, etc.)

- Test results from early prototypes, including system integration experience

- Full irradiation data

- List of changes in the design since the last prototypes produced, with full simulations if applicable

- Fully developed production test plan and schedule

- QA/QC documents (validate reliability of design and construction or manufacturing techniques)

- Procurement plan and procedures

# PRR Documentation

The purpose of the production readiness review (PRR) is to demonstrate overall production readiness and assure that the items to be produced will meet the defined requirements. All necessary production plans, travelers, tools, facilities and other resources shall be in place. Closure of Actions from the previous Reviews is a requirement as well.

The PPR evaluates if

- The design is producible and well documented

- The manufacturing and delivery plan is adequate

- Manufacturing control and production process are developed and tried out

- Adequate resources necessary to execute production, including full rate production and associated capacity issues, have been identified and secured.

Safety aspects are validated at Integration/Readiness for Installation reviews, and do require specific safety documentation that has been validated by CERN HSE and/or ATLAS TC.

Documentation to be made available for the detector/mechanical PRR:

- Complete drawing package for production

- Applicable ECRs

- Procurement strategy, including the adjudication criteria

- Manufacturing, assembly and delivery plan

- Material flow for and after production, logistics plan

- QA/QC at manufacturing, reception and acceptance with the required tools and test infrastructure.

- Organigram of the production management

- Traceability plan (production database in place)

- Schedule

Documentation to be made available for the electronics PRR:

- Complete design package for production (e.g.: schematics, layout including fabrication drawing and gerber, assembly package including assembly drawing and bill of materials, etc.)

- Test results from pre-production, demonstrated QA/QC at planned rate and acceptable yield

- Updated irradiation data

- Procurement strategy, including the adjudication criteria

- Fully developed production manufacturing, assembly and delivery plan and schedule

- Fully developed QA/QC procedure for production test with the required tools and test infrastructure.

- Traceability plan (production database in place)

The documents listed above should be available in EDMS prior to the PRR, for review at the PRR. A structured folder or document with links to the EDMS documents should be provided.

For distributed productions, On-site Production Readiness Reviews can be held by the Review Office on request of the Project Leaders.